## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Planning | 2024-03-01 | 2024-03-10 | 10 | Alex Johnson | On Track
Market Research | 2024-03-11 | 2024-03-25 | 15 | Sarah Chen | In Progress
Design Phase | 2024-03-26 | 2024-04-15 | 21 | Mark Turner | Not Started
Development | 2024-04-16 | 2024-05-31 | 47 | Team A | Planned
Testing & QA | 2024-06-01 | 2024-06-15 | 15 | Lisa Wong | Not Started
Launch Preparation | 2024-06-16 | 2024-06-30 | 15 | David Kim | Not Started
Post-Launch Review | 2024-07-01 | 2024-07-10 | 10 | All Team | Planned