## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | 100 | Project Manager
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | 85 | Business Analyst
UI/UX Design Phase | 2024-03-16 | 2024-04-10 | 25 | 65 | Design Lead
Development (Phase 1) | 2024-04-11 | 2024-05-31 | 51 | 30 | Development Team
Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 30 | 55 | QA Engineer
Deployment & Go-Live | 2024-07-01 | 2024-07-15 | 15 | 25 | IT Operations
Post-Launch Review | 2024-07-16 | 2024-07-20 | 5 | 10 | Project Manager