## Worksheet
Task | Start Date | End Date | Duration (Days) | Status
Project Planning | 2024-04-01 | 2024-04-05 | 5 | In Progress
Requirement Gathering | 2024-04-06 | 2024-04-15 | 10 | Planned
Design Phase | 2024-04-16 | 2024-05-10 | 35 | Not Started
Development | 2024-05-11 | 2024-07-15 | 75 | Scheduled
Testing & QA | 2024-07-16 | 2024-08-15 | 30 | Not Started
Deployment & Go-Live | 2024-08-16 | 2024-08-25 | 10 | Planned
Post-Implementation Review | 2024-08-26 | 2024-08-31 | 6 | Not Started