## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Progress (%) | Responsible Employee
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Completed | 100% | Alex Johnson
Requirement Gathering | 2024-03-02 | 2024-03-15 | 14 | In Progress | 65% | Sarah Chen
Design Phase | 2024-03-16 | 2024-04-05 | 21 | Not Started | 0% | Mike Rodriguez
Development Phase | 2024-04-06 | 2024-05-31 | 57 | Not Started | 0% | Lisa Kim
Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 30 | Not Started | 0% | James Wilson
User Training Session | 2024-07-01 | 2024-07-03 | 3 | Not Started | 0% | Rachel Davis
Project Closure & Review | 2024-07-04 | 2024-07-05 | 2 | Not Started | 0% | Alex Johnson