## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible Person | Dependencies
Project Initiation | 2024-04-01 | 2024-04-05 | 5 | 100 | John Doe | -
Requirements Gathering | 2024-04-06 | 2024-04-15 | 10 | 85 | Jane Smith | Project Initiation
Design Phase | 2024-04-16 | 2024-05-05 | 21 | 60 | Jane Smith | Requirements Gathering
Development Phase | 2024-05-06 | 2024-07-15 | 61 | 30 | Mike Johnson | Design Phase
Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | 25 | 55 | Lisa Brown | Development Phase
Deployment & Launch | 2024-08-11 | 2024-08-15 | 5 | 100 | John Doe | Testing & Quality Assurance