## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | 100 | Manager | Completed
Requirement Gathering | 2024-03-02 | 2024-03-15 | 14 | 75 | Team Lead | In Progress
Design Phase | 2024-03-16 | 2024-03-31 | 16 | 50 | Designer | In Progress
Development Phase | 2024-04-01 | 2024-05-15 | 66 | 30 | Developers | Planned
Testing & QA | 2024-05-16 | 2024-06-10 | 35 | 15 | QA Lead | Not Started
Deployment & Go-Live | 2024-06-11 | 2024-06-15 | 5 | 0 | Operations Manager | Not Started
Post-Launch Review | 2024-06-16 | 2024-06-18 | 3 | 0 | Manager | Not Started