## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible | Status
Project Planning | 2024-04-01 | 2024-04-10 | 10 | 85% | Jane Smith | On Track
Requirement Gathering | 2024-04-11 | 2024-04-25 | 15 | 60% | John Doe | In Progress
Design Phase | 2024-05-01 | 2024-05-15 | 15 | 30% | Lisa Chen | Pending Start
Development | 2024-05-16 | 2024-07-15 | 61 | 10% | Marcus Lee | Delayed
Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | 35 | - | Sara Kim | Not Started
Deployment & Go-Live | 2024-08-11 | 2024-08-15 | 5 | - | Team Lead | Planned