## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Planning | 2024-04-01 | 2024-04-05 | 5 | John Smith | On Track
Requirement Gathering | 2024-04-06 | 2024-04-15 | 10 | Sarah Lee | On Track
Design Phase | 2024-04-16 | 2024-04-28 | 13 | Mike Chen | In Progress
Development | 2024-04-29 | 2024-05-15 | 18 | Team A | Not Started
Testing & QA | 2024-05-16 | 2024-05-31 | 16 | Lisa Wong | Planned
Deployment | 2024-06-01 | 2024-06-05 | 5 | Admin Team | Not Started