## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible Person
Project Kickoff | 2024-04-01 | 2024-04-03 | 3 | 100 | John Smith
Requirement Gathering | 2024-04-04 | 2024-04-15 | 12 | 85 | Sarah Lee
Design Phase | 2024-04-16 | 2024-05-10 | 35 | 60 | Mike Johnson
Development Phase | 2024-05-11 | 2024-07-15 | 75 | 40 | Lisa Chen
Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | 35 | 75 | David Park
Deployment & Launch | 2024-08-11 | 2024-08-15 | 5 | 100 | Emma Rodriguez