## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | Project Management Team | Completed
Market Research & Analysis | 2024-03-16 | 2024-04-10 | 25 | Marketing & Strategy Team | In Progress
Design Phase (UI/UX) | 2024-04-11 | 2024-05-15 | 35 | Design Team | Not Started
Development & Coding | 2024-05-16 | 2024-07-31 | 76 | Engineering Team | Planned
Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | 31 | QA & Operations Team | Not Started
Deployment & Launch | 2024-09-01 | 2024-09-15 | 15 | Operations & IT Team | Not Started
Post-Launch Review & Feedback | 2024-09-16 | 2024-10-10 | 25 | All Teams (Joint) | Not Started