## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Duration (Days)
T101 | Project Planning | 2024-03-01 | 2024-03-15 | Completed | 15
T102 | Design Phase2024-03-16 | 2024-04-10 | In Progress | 35
T103 | Development Phase2024-04-11 | 2024-06-15 | Pending Start | 75
T104 | Testing & QA2024-06-16 | 2024-07-31 | Pending Start | 56
T105 | Deployment & Launch2024-08-01 | 2024-08-31 | Pending Start | 31
Time Management Gantt Chart - Tracking View ¦ Generated for Project Efficiency