## Worksheet
Task | Start Date | End Date | Duration (Days) | Assigned To | Status | Priority
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | John Doe | Completed | High
Market Research Phase | 2024-04-02 | 2024-04-10 | 9 | Jane Smith | In Progress | Medium
Product Design Finalization | 2024-04-11 | 2024-04-20 | 10 | Mike Johnson | Planned | High
Development Sprint 1 | 2024-04-21 | 2024-05-05 | 15 | Team A | In Progress | High
User Testing & Feedback | 2024-05-06 | 2024-05-15 | 10 | Sarah Lee | Planned | Medium
Final Review & Launch | 2024-05-16 | 2024-05-18 | 3 | All Team Members | Completed | High