## Worksheet
Task | Priority | Start Date | End Date | Duration (hrs) | Status | Assigned To
Project Planning Meeting | High | 2024-04-05 | 2024-04-05 | 2 | Completed | Alex Morgan
Develop Project Timeline | High | 2024-04-06 | 2024-04-10 | 4 | In Progress | Sara Chen
Review Budget Allocation | Medium | 2024-04-11 | 2024-04-12 | 2 | Scheduled | David Kim
Team Weekly Sync | Low | 2024-04-15 | 2024-04-15 | 1 | Pending | All Team Members
Finalize Project Deliverables | High | 2024-04-20 | 2024-04-25 | 5 | Not Started | James Reed