## Worksheet
Date | Task Description | Estimated Time (hrs) | Actual Time (hrs) | Time Management Status | Notes
2024-04-01 | Client Meeting – Project Kickoff | 1.5 | 1.75 | On Track | Agreed on timelines and deliverables.
2024-04-03 | Design Wireframes | 4 | 3.5 | On Track | Client approved initial concept.
2024-04-05 | Develop Backend API | 6 | 7.25 | Over Time | Unforeseen third-party integration delay.
2024-04-08 | Frontend UI Implementation | 5 | 4.75 | On Track | All components completed with minor tweaks.
2024-04-10 | Testing and Bug Fixes | 3.5 | 3 | Under Time | No critical bugs found; testing completed early.