## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Time Estimation (hrs) | Progress (%)
T-001 | Project Planning Meeting | John Doe | 2024-04-05 | 2024-04-07 | Completed | Moderate | 2.5 | 100
T-002 | Market Research Analysis | Sarah Kim | 2024-04-08 | 2024-04-15 | In Progress | High | 8 | 65
T-003 | Design Final Review | Mike Johnson | 2024-04-10 | 2024-04-18 | Pending | Moderate | 5.5 | 0
T-004 | Team Training Session | Emma Reed | 2024-04-12 | 2024-04-16 | Completed | Low | 1.5 | 100
T-005 | Client Feedback Collection | David Lee | 2024-04-14 | 2024-04-21 | In Progress | High | 6 | 40