## Worksheet
Task ID | Project Name | Task Description | Assigned To | Start Date | Due Date | Priority Level | Status | Estimated Hours | Actual Hours | Time Remaining | Progress % | Next Action | Notes
T001 | Website Redesign | Redesign homepage and user dashboard with improved UX flow | John Doe | 2024-03-15 | 2024-04-10 | High | In Progress | 8.5 | 6.2 | <2.3 hrs73% | Review UX wireframes with stakeholders | Finalize navigation structure and mobile responsiveness.
T002 | Client Onboarding Process | Develop automated onboarding workflow for new clients | Sarah Lee | 2024-03-20 | 2024-04-15 | Medium | Pending Assignment | 5 | 0 | 5.0 hrs0% | Assign team and set timeline | No client data yet; require access for testing.
T003 | Monthly Reporting Dashboard | Implement real-time KPI tracking with interactive charts | Mike Chen | 2024-03-25 | 2024-04-30 | High | Not Started | 12 | 0 | 12.0 hrs0% | Begin data model design and gather requirements | Need alignment with finance team on key metrics.
T004 | Team Training Session | Conduct workshop on time tracking tools and agile practices | All Team Members | 2024-03-30 | 2024-04-05 | Medium | Scheduled | 3.5 | 3.5 | 0.0 hrs100% | Post-session feedback collection | All participants provided positive feedback.