## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Priority Level | Status | Estimated Hours | Actual Hours | Progress (%) | Next Action Date
T001 | Project Planning Meeting | John Smith | 2024-04-01 | 2024-04-05 | High | Completed | 8 | 8 | 100%
T002 | Design Phase Review | Emily Davis | 2024-04-06 | 2024-04-15 | Medium | In Progress | 12 | 6 | 50% | 2024-04-10
T003 | Develop MVP Features | Michael Brown | 2024-04-16 | 2024-05-10 | High | Not Started | 24 | 0 | 0%
T004 | Client Feedback Session | Sarah Lee | 2024-05-12 | 2024-05-18 | Medium | Scheduled | 4 | 0 | 0% | 2024-05-15
T005 | Final Testing & QA | David Wilson | 2024-05-20 | 2024-06-01 | High | Not Started | 16 | 0 | 0%