## Worksheet
Task | Priority | Due Date | Status | Time Estimate (hrs) | Assigned To | Progress (%)
Project Planning Meeting | High | 2024-04-15 | In Progress | 2.5 | Sarah Chen | 60%
Design Wireframes | High | 2024-04-20 | Not Started | 6 | Mark Johnson | 0%
Develop Backend APIs | Medium | 2024-05-05 | Scheduled | 12 | Alex Rivera | 25%
User Testing Session | Low | 2024-05-10 | Not Started | 4.5 | Lisa Wong | 0%
Final Documentation | Medium | 2024-05-15 | Not Started | 3 | Emma Taylor | 0%