## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Time Estimate (hrs) | Actual Time (hrs) | Priority
T-001 | Project Planning Meeting | Team A | 2024-04-15 | 2024-04-15 | Completed | 2 | 2.5 | High
T-002 | User Requirement Gathering | Team B | <+style="text-align: center;">2024-04-162024-04-18 | In Progress | 8 | 5 | High
T-003 | Design Phase Final Review | Team C | 2024-04-19 | 2024-04-20 | Planned | 6.5 | 0 | Medium
T-004 | Development Sprint 1 | Team A & B | 2024-04-21 | 2024-04-25 | Not Started | 30 | 0 | High
T-005 | Testing & Bug Fixing | Team C | 2024-04-26 | 2024-05-03 | Scheduled | 15 | 0 | High