## Worksheet
Date | Team Member | Task Category | Planned Time (hrs) | Actual Time (hrs) | Time Variance | Status | Notes
2024-04-01 | Anna Smith | Project Planning | 3.5 | 3 | -0.5 | On Track | Preliminary schedule finalized.
2024-04-01 | James Lee | Development | 5 | 6.5 | 1.5 | Over Time | Code review delayed due to integration issues.
2024-04-02 | Sophia Wong | Testing | 4 | 3.5 | -0.5 | On Track | All critical bugs resolved.
2024-04-03 | Michael Brown | Client Meeting | 1.5 | 1.5 | 0 | On Track | Agreed on next phase deliverables.
2024-04-03 | Lena Garcia | Documentation | 2 | 2.5 | 0.5 | Over Time | Expanded user guides to include new features.
Total Planned: |  |  |  | 18 | 17.5
Total Actual: |  |  |  | 17.5 | -0.5