## Worksheet
Task | Start Date | End Date | Duration (days) | Responsible Person | Priority | Status | Dependencies | Milestones
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Project Manager | High | Completed |  | Yes
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | Business Analyst | High | In Progress | Kickoff Meeting
Design Phase | 2024-04-11 | 2024-04-25 | 15 | UX Designer | Medium | Not Started | Requirements Gathering
Development Phase | 2024-04-26 | 2024-05-31 | 36 | Development Team | High | Not Started | Design Phase
Testing & Quality Assurance | 2024-06-01 | 2024-06-15 | 15 | QA Engineer | High | Not Started | Development Phase
User Training & Deployment | 2024-06-16 | 2024-06-30 | 15 | Training Lead | Medium | Not Started | Testing & QA
Post-Implementation Review | 2024-07-01 | 2024-07-05 | 5 | Project Manager | Low | Not Started |  | Yes