## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority
Project Initiation | 2024-04-01 | 2024-04-05 | 5 | Project Manager | Completed | High
Requirement Gathering | 2024-04-06 | 2024-04-15 | 10 | Business Analyst | In Progress | High
Feasibility Study | 2024-04-16 | 2024-04-20 | 5 | Technical Lead | Not Started | Medium
Design Phase | 2024-04-21 | 2024-05-10 | 20 | Design Team | Not Started | High
Development Phase | 2024-05-11 | 2024-07-15 | 65 | Development Team | Not Started | High
Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | 35 | QA Manager | Not Started | High
Deployment Plan | 2024-08-11 | 2024-08-15 | 5 | Operations Lead | Not Started | Medium
Post-Deployment Review | 2024-08-16 | 2024-08-20 | 5 | Project Manager | Not Started | Low