## Worksheet
Month | Project Phase | Key Activities | Start Date | End Date | Responsible Person | Status | Budget Allocation (USD)
January | Initiation & Planning | Scope definition, stakeholder interviews, risk assessment | 01/01/2024 | 01/31/2024 | Project Manager | On Track | 15,000
February | Design & Feasibility | Wireframing, technical feasibility study, prototype development | 02/01/2024 | 02/28/2024 | Design Lead | On Track | 20,000
March | Development (Phase 1) | Core module development, API integration, UI implementation | 03/01/2024 | 03/31/2024 | Engineering Team | On Track | 45,000
April | Development (Phase 2) | Advanced features implementation, user testing, bug fixes | 04/01/2024 | 04/30/2024 | Engineering Team | On Track | 50,000
May | Quality Assurance & Testing | End-to-end testing, performance review, user acceptance testing (UAT) | 05/01/2024 | 05/31/2024 | QA Lead | On Track | 30,000
June | Deployment & Training | Staging environment deployment, user training sessions, documentation | 06/01/2024 | 06/30/2024 | Operations Manager | On Track | 18,000
July | Post-Implementation Review | Feedback collection, process evaluation, KPI tracking setup | 07/01/2024 | 07/31/2024 | Project Manager | On Track | 5,000
August | Annual Review & Planning (Next Year) | Review performance metrics, identify improvements, plan for Q1 2025 | 08/01/2024 | 08/31/2024 | Senior Management | On Track | 10,000
September | Optimization & Scaling | Performance tuning, infrastructure scaling, security audit | 09/01/2024 | 09/30/2024 | DevOps Team | On Track | 25,000
October | Stakeholder Reporting & Communication | Quarterly report generation, team meetings, external updates | 10/01/2024 | 10/31/2024 | Project Manager | On Track | 8,000
November | Internal Process Improvement | Review workflows, update documentation, improve time tracking tools | 11/01/2024 | 11/30/2024 | Operations Team | On Track | 6,000
December | Year-End Closure & Planning | Final project closure, budget review, annual performance report | 12/01/2024 | 12/31/2024 | Project Manager & Finance Lead | On Track | 12,000