## Worksheet
Task | Start Date | End Date | Duration (days) | Responsible Person | Status
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Jane Smith | Completed
Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 | John Doe | In Progress
Design Phase | 2024-03-16 | 2024-03-25 | 10 | Lisa Chen | Pending
Development Phase | 2024-03-26 | 2024-04-15 | 20 | Mike Johnson | Planned
Testing & Quality Assurance | 2024-04-16 | 2024-04-30 | 15 | Sarah Lee | Pending
Deployment & Go-Live | 2024-05-01 | 2024-05-05 | 5 | Tom Wilson | Not Started