## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority | Milestones
Project Initiation | 2024-04-01 | 2024-04-05 | 5 | John Smith | Completed | High | Kick-off meeting, Budget approval
Scope Definition | 2024-04-06 | 2024-04-15 | 10 | Sarah Lee | In Progress | High | Final scope document approved
Resource Allocation | 2024-04-16 | 2024-04-20 | 5 | Mike Johnson | Not Started | Medium | Team assignments finalized
Risk Assessment | 2024-04-21 | 2024-04-25 | 5 | Lisa Wong | Not Started | High | Risk register created
Project Execution Phase | 2024-04-26 | 2024-05-31 | 36 | Project Team | Not Started | Medium | Key deliverables completed by week 4, milestone review at end of month