## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Project Manager | Completed | High
Requirements Gathering | 2024-04-02 | 2024-04-15 | 14 | Business Analyst | In Progress | High
Design Phase | 2024-04-16 | 2024-05-10 | 35 | UI/UX Designer | Planned | Medium
Development Phase | 2024-05-11 | 2024-07-15 | 76 | Development Team | Planned | High
Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | 35 | QA Engineer | Planned | High
Client Review & Final Approval | 2024-08-11 | 2024-08-15 | 5 | Client Representative | Pending | High
Go-Live & Deployment | 2024-08-16 | 2024-08-16 | 1 | Operations Team | Planned | Medium
Project Summary – Client View