## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Status | Responsible | Progress (%)
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | High | Completed | Project Manager | 100
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | High | In Progress | Business Analyst | 60
Design Phase | 2024-04-11 | 2024-04-25 | 15 | Medium | Not Started | UI/UX Designer | 0
Development Phase | 2024-04-26 | 2024-05-31 | 36 | High | Not Started | Development Team | 0
Testing & QA | 2024-06-01 | 2024-06-15 | 15 | High | Not Started | QA Team | 0
Deployment & Launch | 2024-06-16 | 2024-06-16 | 1 | High | Not Started | DevOps Team | 0
Post-Launch Review | 2024-06-17 | 2024-06-17 | 1 | Medium | Not Started | Project Manager | 0