## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Jane Smith | Completed | High
Requirement Gathering | 2024-03-06 | 2024-03-15 | 10 | John Doe | In Progress | High
Design Phase | 2024-03-16 | 2024-03-25 | 10 | Lisa Chen | Pending | Moderate
Development Phase | 2024-03-26 | 2024-04-15 | 20 | Mike Taylor | Not Started | High
Testing & Quality Assurance | 2024-04-16 | 2024-04-30 | 15 | Sarah Lee | Pending | Moderate
Deployment & Go-Live | 2024-05-01 | 2024-05-03 | 3 | Alex Brown | Not Started | High