## Worksheet
Task | Start Date | End Date | Duration (days) | Priority | Responsible Person | Status | Dependencies
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | High | Project Manager | Not Started
Requirement Gathering | 2024-04-02 | 2024-04-15 | 14 | High | Business Analyst | In Progress | Kickoff Meeting
Design Phase | 2024-04-16 | 2024-05-10 | 25 | Medium | UI/UX Designer | Not Started | Requirement Gathering Complete
Development Phase | 2024-05-11 | 2024-07-15 | 65 | High | Development Team | Not Started | Design Phase Complete
Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | 35 | High | QA Manager | Not Started | Development Phase Complete
Deployment & Go-Live | 2024-08-11 | 2024-08-15 | 5 | Critical | IT Operations Team | Not Started | Testing Complete
Post-Deployment Review | 2024-08-16 | 2024-08-17 | 2 | Medium | Project Manager | Not Started