## Worksheet
Task | Start Date | End Date | Duration (Days) | Assigned To | Status | Progress (%)
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | John Smith | Completed | 100
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | Anna Lee | In Progress | 60
Design Phase | 2024-04-11 | 2024-04-25 | 15 | Mike Chen | Not Started | 0
Development Phase (Phase 1) | 2024-04-26 | 2024-05-15 | 21 | Sarah Kim | Not Started | 0
Testing & Quality Assurance | 2024-05-16 | 2024-05-31 | 16 | David Ross | Not Started | 0
Final Review & Sign-off | 2024-06-01 | 2024-06-03 | 3 | Project Manager | Not Started | 0