## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Responsible Person | Status | Milestones | Dependencies | Allocated Hours/Week
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | High | Project Manager | Completed | Meeting scheduled and conducted |  | 5
Requirements Gathering | 2024-04-02 | 2024-04-15 | 14 | High | Business Analysts | In Progress | Finalize user stories and scope document | Project Kickoff Meeting | 10
Design Phase | 2024-04-16 | 2024-05-10 | 25 | Medium | UX Designer & Dev Team | Not Started | Wireframes, UI mockups approved | Requirements Gathering Complete | 15
Development Phase | 2024-05-11 | 2024-07-31 | 82 | High | Development Team | Not Started | Core modules implemented and tested | Design Phase Complete | 20
Testing & Quality Assurance | 2024-08-01 | 2024-08-15 | 15 | High | QA Team | Not Started | Bug resolution and regression testing complete | Development Phase Complete | 10
Deployment & Go-Live | 2024-08-16 | 2024-08-18 | 3 | Critical | IT Operations Team | Not Started | System goes live with minimal downtime | Testing Complete & Approval Received | 5
Post-Launch Review & Feedback Collection | 2024-08-19 | 2024-08-31 | 13 | Medium | Project Manager & Stakeholders | Not Started | Evaluate performance and user feedback |  | 5