## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Responsible Person | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | HIGH | Jane Smith | Completed
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | HIGH | John Doe | In Progress
Design Phase - Wireframes | 2024-04-11 | 2024-04-18 | 8 | MEDIUM | Lisa Chen | Pending
Development - Frontend | 2024-04-19 | 2024-05-15 | 28 | HIGH | Marcus Lee | Not Started
Development - Backend | 2024-05-16 | 2024-06-10 | 35 | HIGH | Sophia Kim | Not Started
Testing & Bug Fixes | 2024-06-11 | 2024-06-30 | 20 | HIGH | David Brown | Not Started
Client Review & Feedback | 2024-07-01 | 2024-07-05 | 5 | HIGH | Jane Smith | Not Started
Final Delivery & Sign-off | 2024-07-06 | 2024-07-06 | 1 | HIGH | All Team Members | Not Started