## Worksheet
Task | Start Date | End Date | Duration | Responsible Person | Status | Priority | Dependencies
Project Kickoff Meeting | 01/03/2024 | 01/03/2024 | 1 day | Project Manager | Completed | High | None
Market Research & Analysis | 02/03/2024 | 05/03/2024 | 15 days | Marketing Lead | In Progress | High | Kickoff Meeting
Product Design Finalization | 06/03/2024 | 15/03/2024 | 10 days | UI/UX Designer | Not Started | High | Market Research
Development Phase - Phase 1 | 16/03/2024 | 30/03/2024 | 15 days | Development Team | Not Started | High | Product Design Finalization
Testing & Quality Assurance | 01/04/2024 | 15/04/2024 | 15 days | QA Engineer | Not Started | High | Development Phase - Phase 1
Final Review & Client Presentation | 16/04/2024 | 18/04/2024 | 3 days | Project Manager | Not Started | High | Testing & QA