## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority | Dependencies
Project Initiation | 2024-04-01 | 2024-04-05 | 5 | John Smith | Completed | High
Requirements Gathering | 2024-04-06 | 2024-04-15 | 10 | Sarah Lee | In Progress | High | Project Initiation
Design Phase | 2024-04-16 | 2024-05-05 | 20 | Mike Chen | Planned | Medium | Requirements Gathering
Development Phase | 2024-05-06 | 2024-07-15 | 60 | Team A (Dev) | Not Started | High | Design Phase
Testing & QA | 2024-07-16 | 2024-08-10 | 35 | Lisa Wong | Planned | High | Development Phase
Deployment & Launch | 2024-08-11 | 2024-08-15 | 5 | Raj Patel | Not Started | Critical | Testing & QA