## Project Plan - Time Management
Task ID | Task Name | Description | Start Date | End Date th> | Duration (Days) | Responsible Person th> | Status
T101 | Project Kickoff Meeting | Define project scope, objectives, and initial timelines. | 2024-03-01 | 2024-03-01 | 1 | Jane Smith | In Progress
T102 | Scope Definition & Stakeholder AlignmentFinalize project scope, gather stakeholder input, and document requirements. 2024-03-02 2024-03-15 | 14 | Marcus Lee | Planned
T103 | Resource Allocation PlanDetermine team members, tools, and budget allocation. 2024-03-16 2024-03-20 | 5 | Sarah Chen | Pending
T104 | Risk Assessment & Mitigation StrategyIdentify potential risks and develop mitigation plans. 2024-03-21 2024-03-25 | 5 | Alex Rodriguez | Pending
T105 | Initial Timeline Development (Gantt)Create preliminary Gantt chart and schedule milestones. 2024-03-26 2024-04-03 | 8 | Lisa Wong | In Progress
T106 | Project Review & Approval Workflow SetupEstablish review cycles and approval processes for deliverables. 2024-04-04 2024-04-10 | 7 | Jane Smith | Planned
T107 | Daily Stand-up Implementation PlanSchedule and document daily stand-up meetings. 2024-04-11 2024-05-31 | 183 | Marcus Lee | Pending
T108 | Weekly Progress Reporting Template Design<Create standardized weekly report format for team and leadership. 2024-04-15 2024-05-15 | 31 | Sarah Chen | In Progress
T109 | Time Tracking System IntegrationIntegrate team time tracking tools into project workflow. 2024-05-16 2024-06-30 | 45 | Alex Rodriguez | Pending
T110 | Final Project Closeout & Lessons LearnedDocument outcomes, challenges, and recommendations for future projects. 2024-07-01 2024-07-15 | 15 | Lisa Wong | Pending
Total Tasks: |  |  |  | 10 | Total Duration (Days): | 369