## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority
Project Initiation & Planning | 01/01/2024 | 01/15/2024 | 15 | John Smith | In Progress | High
Requirements Gathering | 01/16/2024 | 02/05/2024 | 19 | Sarah Johnson | On Track | High
Design Phase (UI/UX) | 02/06/2024 | 03/15/2024 | 40 | Mike Brown | Planned | Medium
Development Phase | 03/16/2024 | 06/30/2024 | 115 | Team A (Dev) | On Track | High
Testing & Quality Assurance | 07/01/2024 | 08/15/2024 | 55 | Lisa Davis | Not Started | High
Deployment & Go-Live | 08/16/2024 | 08/31/2024 | 16 | Admin Team | Not Started | Critical
Post-Launch Review & Feedback | 09/01/2024 | 09/30/2024 | 30 | Project Manager | Planned | Low