## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Project Manager | Completed | High
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | Business Analyst | In Progress | High
Design Phase | 2024-04-11 | 2024-04-25 | 15 | UX Designer | Planned | Medium
Development Phase | 2024-04-26 | 2024-05-30 | 35 | Development Team | Not Started | High
Testing & QA | 2024-06-01 | 2024-06-15 | 15 | QA Lead | Not Started | High
Deployment & Training | 2024-06-16 | 2024-06-30 | 15 | IT Operations | Not Started | Medium
Post-Implementation Review | 2024-07-01 | 2024-07-05 | 5 | Project Manager | Planned | Low