## Worksheet
Task | Start Date | End Date | Duration | Responsible Person | Priority | Status | Dependencies
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 day | John Smith | High | Completed
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 days | Sarah Lee | High | In Progress | Kickoff Meeting
Design Phase | 2024-04-11 | 2024-04-25 | 15 days | Mike Chen | Medium | Not Started | Requirements Gathering
Development Phase | 2024-04-26 | 2024-05-31 | 36 days | Team A | High | Not Started | Design Phase
Testing & Quality Assurance | 2024-06-01 | 2024-06-15 | 15 days | Lisa Wong | High | Not Started | Development Phase
Project Review & Delivery | 2024-06-16 | 2024-06-16 | 1 day | John Smith | High | Not Started | Testing & QA