## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Priority | Status
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | John Smith | High | In Progress
Requirement Gathering | 2024-03-06 | 2024-03-15 | 10 | Sarah Lee | High | Not Started
Design Phase | 2024-03-16 | 2024-03-28 | 13 | Mike Johnson | Medium | Planned
Development & Testing | 2024-03-29 | 2024-04-30 | 32 | Team Lead | High | Not Started
Deployment & Training | 2024-05-01 | 2024-05-10 | 10 | Lisa Wong | Medium | Planned
Post-Implementation Review | 2024-05-11 | 2024-05-15 | 5 | John Smith | Low | Not Started