## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | John Doe | Completed
Scope Definition | 2024-03-06 | 2024-03-15 | 10 | Jane Smith | In Progress | Project Initiation
Resource Allocation | 2024-03-16 | 2024-03-20 | 5 | Mike Johnson | Not Started | Scope Definition
Risk Assessment | 2024-03-21 | 2024-03-27 | 7 | Sarah Lee | Planned | Resource Allocation
Project Execution | 2024-03-28 | 2024-04-15 | 20 | Team Lead | Not Started | Risk Assessment