## Worksheet
Task | Start Date | End Date | Duration (days) | Responsible Person | Status
Project Initiation | 2024-04-01 | 2024-04-05 | 5 | John Doe | Completed
Requirements Gathering | 2024-04-06 | 2024-04-15 | 10 | Jane Smith | In Progress
Design Phase | 2024-04-16 | 2024-04-25 | 10 | Alex Johnson | Planned
Development Phase | 2024-04-26 | 2024-05-15 | 20 | Team A | Not Started
Testing & QA | 2024-05-16 | 2024-05-30 | 15 | Sarah Lee | Not Started
Deployment & Training | 2024-06-01 | 2024-06-10 | 10 | Mike Brown | Planned