## Worksheet
Task | Start Date | End Date | Duration | Responsible Person | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 day | John Smith | Completed
Market Research & Analysis | 2024-04-02 | 2024-04-10 | 9 days | In Progress | Planned
Develop Project Timeline | 2024-04-11 | 2024-04-15 | 5 days | Sarah Lee | Pending
Design Brand Identity | 2024-04-16 | 2024-04-25 | 10 days | Mike Johnson | Not Started
Finalize Product Specifications | 2024-04-26 | 2024-05-03 | 8 days | Lisa Wong | Planned
Launch Preparation Meeting | 2024-05-04 | 2024-05-04 | 1 day | John Smith | Pending