## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies
Product Vision Finalization | Sarah Chen | 2024-03-01 | 2024-03-15 | 15 | High | In Progress | None
Market Research & Competitor Analysis | David Kim | <2024-03-16 | 2024-03-31 | 16 | High | Planned | Product Vision Finalization
MVP Feature Prioritization | Lena Torres | 2024-04-01 | 2024-04-15 | 15 | High | Not Started | Market Research & Competitor Analysis
UI/UX Design Phase | James Reed | 2024-04-16 | 2024-05-10 | 25 | Medium | Planned | MVP Feature Prioritization
Frontend Development (Phase 1) | Aisha Patel | 2024-05-11 | 2024-06-05 | 35 | High | Not Started | UI/UX Design Phase
Backend Integration & API Setup | Michael Brown | 2024-06-06 | 2024-07-15 | 40 | High | Not Started | Frontend Development (Phase 1)
Beta Testing & User Feedback Loop | Team Lead | 2024-07-16 | 2024-08-10 | 35 | Medium | Not Started | Backend Integration & API Setup
Final Launch & Go-To-Market Strategy | CEO | 2024-08-11 | 2024-08-31 | 21 | High | Not Started | Beta Testing & User Feedback Loop