## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Sarah Johnson | Completed | High
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | Mike Chen | In Progress | High
Design Phase (Wireframes) | 2024-04-11 | 2024-04-18 | 8 | Lisa Park | Planned | Medium
Development Sprint 1 | 2024-04-19 | 2024-05-03 | 16 | Team A (Dev) | Not Started | High
Testing & Quality Assurance | 2024-05-04 | 2024-05-17 | 14 | David Ruiz | Not Started | High
Final Review & Sign-off | 2024-05-18 | 2024-05-18 | 1 | Project Manager | Not Started | Critical