## Worksheet
Task | Owner | Start Date | End Date | Duration (days) | Status | Dependencies | Priority
Project Kickoff Meeting | Sarah Johnson | 2024-04-01 | 2024-04-01 | 1 | Completed | - | High
Requirements Gathering | Mark Thompson | 2024-04-02 | 2024-04-10 | 9 | In Progress | Kickoff Meeting | High
Design Phase | Lena Chen | 2024-04-11 | 2024-04-25 | 15 | Planned | Requirements Gathering | Medium
Development Phase | Team A (Dev) | 2024-04-26 | 2024-05-30 | 35 | Not Started | Design Phase | High
Testing & Quality Assurance | David Ruiz | 2024-06-01 | 2024-06-15 | 15 | Planned | Development Phase | High
User Training & Documentation | Claire Moore | 2024-06-16 | 2024-06-25 | 10 | Not Started | Testing & QA | Medium
Project Review & Closure | Sarah Johnson | 2024-06-26 | 2024-06-30 | 5 | Not Started | User Training | Low