## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Project Manager | Completed | High
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | Business Analyst | In Progress | High
Design Phase | 2024-04-11 | 2024-04-25 | 15 | UI/UX Designer | Planned | Medium
Development Phase (Phase 1) | 2024-04-26 | 2024-05-15 | 21 | Software Engineer Team | Scheduled | High
Testing & Quality Assurance | 2024-05-16 | 2024-05-31 | 16 | QA Manager | Planned | High
Deployment & Go-Live | 2024-06-01 | 2024-06-03 | 3 | IT Operations Team | Scheduled | High
Post-Deployment Review | 2024-06-04 | 2024-06-05 | 2 | Project Manager | Planned | Low
Template Version - Project Plan for Time Management