## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible | Progress (%) | Dependencies
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Completed | Project Manager | 100
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | In Progress | Business Analyst | 60 | Kickoff Meeting
Design Phase | 2024-04-11 | 2024-04-25 | 15 | Planned | UI/UX Designer | 0 | Requirements Gathering
Development Phase | 2024-04-26 | 2024-05-31 | 36 | Not Started | Development Team | 0 | Design Phase
Testing & Quality Assurance | 2024-06-01 | 2024-06-15 | 15 | Planned | QA Lead | 0 | Development Phase
Project Review & Deployment | 2024-06-16 | 2024-06-18 | 3 | Not Started | Project Manager | 0 | Testing & QA