## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Status | Assigned To | Dependencies | Notes
Project Planning & Scope Definition | 2024-03-01 | 2024-03-07 | 7 | High | In Progress | Project Manager | - | Finalize deliverables and stakeholder expectations.
Resource Allocation & Team Assignment | 2024-03-08 | 2024-03-14 | 7 | Medium | Not Started | Team Lead | Project Planning Complete | Assign roles based on skill sets and availability.
Requirement Gathering & Analysis | 2024-03-15 | 2024-03-28 | 14 | High | In Progress | Business Analyst | Project Planning & Resource Allocation | Conduct interviews and workshops with stakeholders.
Design & Wireframing | 2024-03-29 | 2024-04-10 | 12 | Medium | Not Started | UX Designer | Requirement Gathering Complete | Create user flows and interface mockups.
Development & Coding | 2024-04-11 | 2024-05-30 | 50 | High | Not Started | Development Team | Design & Wireframing Complete | Implement features according to design specifications.
Testing & Quality Assurance | 2024-06-01 | 2024-06-15 | 15 | High | Not Started | QA Team | Development Complete | Conduct unit, integration, and user acceptance testing.
Deployment & Go-Live | 2024-06-16 | 2024-06-18 | 3 | Critical | Not Started | DevOps Engineer | Testing & QA Complete | Deploy to production environment with rollback plan.
Post-Deployment Review & Feedback | 2024-06-19 | 2024-06-25 | 7 | Medium | Not Started | Project Manager | Deployment Complete | Gather user feedback and document lessons learned.