## Worksheet
Month | Project Goal | Key Tasks | Start Date | End Date | Priority Level | Responsible Person | Progress (%)
January | Project Initiation & Planning | Define scope, identify stakeholders, finalize project plan | 2024-01-01 | 2024-01-31 | High | Project Manager | 85%
February | Resource Allocation & Team Setup | Assign team members, schedule meetings, secure tools | 2024-02-01 | 2024-02-28 | High | HR & Operations Lead | 90%
March | Design & Prototyping Phase | Create wireframes, conduct user testing, refine design | 2024-03-01 | 2024-03-31 | Medium | Design Director | 75%
April | Development & Coding Phase | Build core features, integrate APIs, perform QA | 2024-04-01 | 2024-04-30 | High | Lead Developer | 65%
May | Testing & Bug Fixing | Conduct end-to-end testing, resolve critical bugs | 2024-05-01 | 2024-05-31 | High | QA Manager | 95%
June | Staging & User Acceptance | Deploy to staging, gather user feedback, conduct UAT | 2024-06-01 | 2024-06-30 | Medium | Product Owner | 80%
July | Final Review & Deployment | Finalize documentation, perform last checks, go live | 2024-07-01 | 2024-07-31 | High | Project Manager | 98%
August | Post-Launch Monitoring | Track performance, collect analytics, identify improvements | 2024-08-01 | 2024-08-31 | Low | Operations Team | 70%
September | Feedback Analysis & Reporting | Compile user feedback, generate performance report | 2024-09-01 | 2024-09-30 | Medium | Business Analyst | 85%
October | Q4 Planning & Roadmap Update | Develop next phase goals, allocate resourcesPlan for Q4 initiatives, review performance metrics | 2024-10-01 | 2024-10-31 | Medium | Strategy Lead | 78%
November | Team Training & Knowledge Transfer | Conduct training sessions, document processes | 2024-11-01 | 2024-11-30 | Medium | Mentor & Trainer | 88%
December | Annual Review & Closing | Conduct project closure meeting, archive data, celebrate success | 2024-12-01 | 2024-12-31 | Low | Project Manager & Team | 95%