## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Responsible Person | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | High | Project Manager | Completed
Requirements Gathering | 2024-04-02 | 2024-04-15 | 14 | High | Business Analyst | In Progress
Design Phase | 2024-04-16 | 2024-05-10 | 25 | Medium | UI/UX Designer | Planned
Development Phase | 2024-05-11 | 2024-07-31 | 82 | High | Development Team | Not Started
Testing & Quality Assurance | 2024-08-01 | 2024-08-20 | 20 | High | QA Lead | Planned
Project Review & Final Approval | 2024-08-21 | 2024-08-21 | 1 | Critical | Project Manager | Not Started